## Operational Risks (Update)
|  |  | Risk assessment |  |  | Risk treatment
ID | Category | Area | Event | Impact | Probability | Risk Score before treatment | Proposed treatment | Mitigation | Risk owner | Impact after extra controls | Probability after extra controls | Risk score after extra controls
1 | Operationl Risk | Inventory Management | Excess inventory holding costs or stockouts | High | High | 3 | Reduce | Use of ERP-System to track products in stock, expiry dates, etc. | Harry | Medium | Low | 1
2 | Operationl Risk | Supply Chain Management | Stockouts and operational slowdowns | High | Medium | 2 | Reduce | Develop a resilient supply chain strategy that includes multiple suppliers, geographic diversification, and contingency planning for alternative transportation routes. | Cathy | High | Low | 1
3 | Technology Risk | Cyber Security | Damage, or theft of sensitive data | Very High | High | 4 | Reduce | Enhanced security measures, such as implementing multi-factor authentication (MFA), data encryption, and role-based access control (RBAC) | Alice/Cathy | Medium | Low | 1
4 | Technology Risk | Data Managment & Governance | Data inaccuracies, loss, and regulatory non-compliance | Medium | Medium | 2 | Reduce | Strengthening DG and regularly patching systems are recommended to ensure compliance, protect sensitive information, maintain operational continuity | Alice/Cathy | High | Low | 1
5 | Strategic Risk | Market Dependecy | Revenue loss, and vulnerability to market fluctuations or downturns | Very High | High | 4 | Reduce | Enhance resilience with energy-efficient technologies and compliance with data regulations to maintain profitability. | Cathy | Medium | Medium | 2
6 | Strategic Risk | Inefficiencies | Increased costs, and reduced productivity, financial losses and decreased competitiveness | Medium | Medium | 2 | Reduce | Prepare for external risks with flexible pricing, digital transformation incentives, and a disaster recovery plan. | Cathy | Low | Low | 1
Assessment Part 2: Assessment of Potential Digital Transformations
The risks listed below will also materialise if the company decides to address the strategic questions posed by Cathrin (e-commerce and internal supply chains).
|  |  | Risk assessment |  |  | Risk treatment
ID | Area | Proposed Change | Event | Impact | Probability | Risk Score before treatment | Proposed treatment | Mitigation | Risk owner | Impact after extra controls | Probability after extra controls | Risk score after extra controls
1 | Operational | ERP | CIA Breach | High | Medium | 2 | Reduce | Encryption, MFA, and strong access controls, data validation checks, secure coding practices, patching, data redudency. |  | High | Low | 1
2 | Operational | ERP | CIA Breach | High | Medium | 2 | Reduce | Encryption, MFA, and strong access controls, data validation checks, secure coding practices, patching, data redudency. |  | High | Low | 1
3 | Cyber Security | MFA, RBAC | CIA Breach | High | Medium | 2 | Reduce | Encryption, MFA, and strong access controls, data validation checks, secure coding practices, patching, data redudency. |  | High | Low | 1
4 | Cyber Security | DLP, DAR & DIT Encryption | CIA Breach | High | Medium | 2 | Reduce | Encryption, MFA, and strong access controls, data validation checks, secure coding practices, patching, data redudency. |  | High | Low | 1
5 | Cyber Security | High Availabiliy (HA) Networks | CIA Breach | Medium | Medium | 2 | Reduce | Encryption, MFA, and strong access controls, data validation checks, secure coding practices, patching, data redudency. |  | Medium | Low | 1
6 | Strategic | E-Commerce Platform.ERP, CRM | CIA Breach | High | Medium | 2 | Reduce | Encryption, MFA, and strong access controls, data validation checks, secure coding practices, patching, data redudency. |  | High | Low | 1
7 | Strategic | DLP, Compliance Management Software: | CIA Breach | Medium | Medium | 2 | Reduce | Encryption, MFA, and strong access controls, data validation checks, secure coding practices, patching, data redudency. |  | Medium | Low | 1
8 | Strategic | Business Intelligence (BI) and Analytics, Digital Transformation Incentives | CIA Breach | Medium | Medium | 2 | Reduce | Encryption, MFA, and strong access controls, data validation checks, secure coding practices, patching, data redudency. |  | Medium | Low | 1

## Operational Risks
|  |  | Risk assessment |  |  | Risk treatment
ID | Area | Event | Impact | Probability | Risk Score before treatment | Proposed treatment | Mitigation | Risk owner | Impact after extra controls | Probability after extra controls | Risk score after extra controls
1 | Inventory Management | Overview of inventory is lost | High | Medium | 2 | Eliminate | Use of ERP System to track products in stock, expiry dates, etc. | Harry | Medium | Low | 1
2 | Inventory Management | Damage to inventory (water, fire, earthquake) | Very High | Low | 2 | Eliminate | Insurance | Cathy | Medium | Low | 1
3 | Inventory Management | Loss of inventory (contamination, mishandling, wrong storaging) | Very High | Low | 2 | Reduce | Reocurring professional cleaning, professional storaging, heating/cooling, humidity | Harry | Medium | Low | 1
4 | Inventory Management | Inaccurate forecasting | Medium | Medium | 2 | Reduce | Use of ERP System with prediction functionality | Harry | Medium | Low | 1
5 | Inventory Management | Inventory loss (theft) | High | Medium | 2 | Reduce | Security cameras, professional access system, insurance | Harry | Medium | Low | 1
6 | Inventory Management | Lack of supply | Medium | Medium | 2 | Reduce | Automated reordering as soon as a threshold value is undershot | Harry | Medium | Low | 1
7 | Supply Chain Management | Current supplier fails | Very High | Medium | 3 | Reduce | Use of multiple suppliers | Cathy | Low | Low | 1
8 | Supply Chain Management | Supply chain disruption | High | Medium | 2 | Reduce | Use of multiple suppliers | Cathy | Low | Low | 1
9 | Supply Chain Management | Quality of sourced ingredients | High | Medium | 2 | Reduce | Setup of QA for ingredients | Cathy | Low | Low | 1
10 | Supply Chain Management | Inflation | High | Low | 1 | Reduce | Long term contracts with price fixing | Cathy | Medium | Low | 1
11 | Supply Chain Management | Reputational risk | Medium | Low | 1 | Reduce | Use clause in contracts | Cathy | Low | Low | 1
12 | Strategic Risk | Market Dependency | Medium | Medium | 2 | Reduce | Exploring sales channels to reduce dependence | Alice/Cathy | Low | Low | 1
13 | Strategic Risk | Market Competition | Medium | Medium | 2 | Reduce | Conduct research on the market before expanding | Alice/Cathy | Low | Low | 1
14 | Strategic Risk | Customer Relationship Disruption | Medium | Medium | 2 | Reduce | To use hybrid model in person interaction alongside providing extra digital services | Cathy | Low | Low | 1
15 | Cyber Security Risk | Shared Network | High | High | 3 | Eliminate | separate wireless network from computers network | Alice/Cathy | Low | Low | 1
16 | Cyber Security Risk | Outdated Computer software | High | High | 3 | Eliminate | update software | Alice/Cathy | Low | Low | 1
17 | Cyber Security Risk | standalone computer with no DR | High | High | 3 | Eliminate | use cloud based applications to keep backup for data | Alice/Cathy | Medium | Low | 1
18 | Cyber Security Risk | Customer Data | High | Medium | 2 | Reduce | Enforce cybersecurity measures to safeguard customer data and trust | Alice/Cathy | Medium | Low | 1
Assessment Part 2: Assessment of Potential Digital Transformations
The risks listed below will also materialise if the company decides to address the strategic questions posed by Cathrin (e-commerce and internal supply chains).
|  |  | Risk assessment |  |  | Risk treatment
ID | Area | Event | Impact | Probability | Risk Score before treatment | Proposed treatment | Mitigation | Risk owner | Impact after extra controls | Probability after extra controls | Risk score after extra controls
1 | Inventory Management | Overview of inventory is lost | High | Medium | 2 | Eliminate | Connect ERP system to CRM system and e-commerce shop | Harry | Medium | Low | 1
2 | Supply Chain Management | Complex regulatory environments | High | Medium | 2 | Reduce | Relationship management with suppliers and authorities, contractual clauses | Cathy | Medium | Low | 1
3 | Supply Chain Management | Geopolitical risks | High | Medium | 2 | Reduce | Use a multi supplier strategie | Cathy | Medium | Low | 1
4 | Supply Chain Management | Economic instability | High | Low | 1 | Reduce | Use a multi supplier strategie | Cathy | Low | Low | 1
5 | Supply Chain Management | Natural disasters | High | Low | 1 | Reduce | Use a multi supplier strategie | Cathy | Low | Low | 1
6 | Cyber Security Risk | Hacking, Phishing & Ransomware | High | High | 3 | Reduce | Implementing multi-layered security measures | Alice/Cathy | Medium | Low | 1
7 | System Downtime | System Downtime, disrupting operations | High | Medium | 2 | Reduce | Regular system backups and a comprehensive disaster recovery plan | Alice/Cathy | Medium | Low | 1
8 | E-Commerce | Payment fraud and dissatisfaction due to user experience issues | High | Medium | 2 | Reduce | Ensure a robust hosting , secure payment gateways, and a user-friendly interface | Alice/Cathy | Medium | Low | 1
9 | Strategic Risk | Customer Relationship Disruption | High | Medium | 2 | Reduce | To use hybrid model in person interaction alongside providing extra digital services | Alice/Cathy | Medium | Low | 1
10 | Strategic Risk | Improving Sales Channels | High | Medium | 2 | Reduce | Establishing e-commerce, ERP, social media integration | Alice/Cathy | Medium | Low | 1
11 | Strategic Risk | Market Analysis | High | Medium | 2 | Reduce | Performing market analysis, improve customer customer loyalty programs | Alice/Cathy | Medium | Low | 1
12 | Strategic Risk | Market Dependency | High | Medium | 2 | Reduce | Exploring sales channels to reduce dependence | Alice/Cathy | Medium | Low | 1

## RiskMatrix
Impact | Very High (4) | Medium (2) | High (3) | Very High (4) | Very High (4)
| High (3) | Low (1) | Medium (2) | High (3) | Very High (4)
| Medium (2) | Low (1) | Medium (2) | Medium (2) | High (3)
| Low (1) | Low (1) | Low (1) | Medium (2) | Medium (2)
|  | Low (1) | Medium (2) | High (3) | Very High (4)
Probability

## Data
Impact | Proposed Treatment | Risk Probability | Impact | Very High | 2 | 3 | 4 | 4
Low | Eliminate | Low |  | High | 1 | 2 | 3 | 4
Medium | Tolerate | Medium |  | Medium | 1 | 2 | 2 | 3
High | Reduce | High |  | Low | 1 | 1 | 2 | 2
Very High | Transfer | Very High |  |  | Low | Medium | High | Very High
Probability